## Master
IPNI Tactical Planning Template - WG8 contribution |  |  |  | Mid-term Report suggested for June 2016
Theme | Issue or desired outcome | Strategy | Regions | Deliverables | Date | Lead | Partners | Funding
Defining soybean nutrient management for low-yielding areas | Nutrient consumption is presently low or unbalanced in some soybean regions and needs adjustments. Desired outcome is to develop nutrient use strategies to increase soybean yield by improving nutrient efficiency | Set nutrient omission plots to determine the amount of NPK required attaining a defined yield target. | China | Articles for BC China, and BC | 2015 | China: Ping | Universities, farmers, research institutes | WG8, regional budgets, others. Possible involvement from MC's
|  |  | China | Peer.review publication | 2016 | China: Ping | Universities, farmers, research institutes | WG8, regional budgets, others. Possible involvement from MC's
|  |  | South Asia | Articles for BC India, and BC | 2016 | India: Kaushik. | Universities, farmers, research institutes | WG8, regional budgets, others. Possible involvement from MC's
|  |  | South Asia | Peer.review publication | 2017 | India: Kaushik. | Universities, farmers, research institutes | WG8, regional budgets, others. Possible involvement from MC's
|  | Set validation trials to adjust the amount of NPK required to attain a defined yield target | Russia | Articles for Newsletter Russia, and BC | 2016 and 2017 | Central Russia: Svetlana; South & East Russia: Vladimir. | Universities, farmers, research institutes | WG8, regional budgets, others. Possible involvement from MC's
|  |  | Russia | Peer.review publication | 2017 | Central Russia: Svetlana; South & East Russia: Vladimir. | Universities, farmers, research institutes | WG8, regional budgets, others. Possible involvement from MC's
Educating farmers and agronomists in soybean management and fertilization | In several soybean production regions, there is a need for information on nutrient deficiencies and basic nutrient and crop management information | Develop extension materials | Africa | Format and reprint "Be your own soybean doctor" and "How a soybean plant develops?" | 3/2015 | Shamie, J. Mutegi | IPNI | WG8, regional budgets, possible local sponsors
|  |  |  | • Booklets and brochures on fertilizer BMPs for Africa | 11/2014 | Shamie, J. Mutegi | Universities and research institutes, farmers associations, MCs and other companies | WG8, regional budgets, possible local sponsors
|  |  | South Asia | Format and reprint "Be your own soybean doctor" and "How a soybean plant develops?" | 3/2015 | Kaushik | IPNI | WG8, regional budgets, possible local sponsors
|  |  |  | • Booklets and brochures on fertilizer BMPs for India | 6/2015 | Kaushik | Universities and research institutes, farmers associations, MCs and other companies | WG8, regional budgets, possible local sponsors
|  |  | Russia | • Booklets and brochures on fertilizer BMPs for Russia | 6/2017 | Svetlana and Vladimir | Universities and research institutes, farmers associations, MCs and other companies | WG8, regional budgets, possible local sponsors
Closing yield gap between current and attainable yields in high-yielding regions | In high-yielding regions, there is a need to explore nutrient management and its interactions with crop management practices to reduce the yield gap between current and attainable yields. Desired outcome is to develop a better fertilizer recommendation to increase soybean yields | Set field trials to evaluate crop and nutrition management practices, and to determine the contribution of biological fixation | Argentina, Brazil, and United States | Articles for IAH and BC | 6/2015 and 6/2016 | Argentina: Fernando; Brazil: Eros; United States: Mike. | KSU, MT Foundation, INTA, FCA-UNR | WG8, regional budgets, others. Possible involvement from MC's and other companies, Interaction with WG4
|  |  | Argentina, Brazil, and United States | Peer-review publication | 6/2017 | Argentina: Fernando; Brazil: Eros; United States: Mike. | KSU, MT Foundation, INTA, FCA-UNR | WG8, regional budgets, others. Possible involvement from MC's and other companies, Interaction with WG4
| Defining N management for high-yielding systems | Set field trials to determine the contribution of biological fixation under contrasting management situations | Argentina, Brazil, and United States | Peer-review paper on Biological N fixation in soybeans | 7/2016 | Argentina: Fernando; Brazil: Eros; United States: Mike. | KSU, MT Foundation, INTA, FCA-UNR | WG8, regional budgets, others. Possible involvement from MC's and other companies, Interaction with WG4
Describe the yield gap among regions based on the characterization of soybean systems | Provide information on soybean yield gaps between current and attainable yields Desired outcome is to develop a portal website that gather information related to the soybean cropping systems around the globe, as well as, research reports and materials related to the 4R Nutrient Stewardship | Collection of data from commercial fields and improved management in different regions. Compilation of regional information on advances in soybean nutrient management | All | Develop portal website with information regarding soybean. | 2014-2016 | Eros and Fernando | IPNI programs | WG8